Riverside cutover — go-live runbook

Exported from Notion · Halden Freight operations wiki · last edited 2026-10-02 by Ana Ruiz

Scope

Move all picking, packing and dispatch at the Riverside warehouse from the legacy system to the new warehouse system. Cutover date: October 21, 2026 (moved from October 14 after the scanner vendor delay).

Go-live risks

1. Label printer firmware. The twelve label printers must be upgraded to firmware v4.2 before go-live, or pick tickets print blank. Owner: Cara Lind with the printer vendor.

2. Handheld scanner delivery. Handhelds arrive October 16; any further slip moves the cutover again.

3. Carrier pickups. Carriers must be told the new date one week ahead (done by Ana Ruiz on 2026-09-29).

Rollback

If more than 2 percent of orders fail to print or scan on day one, switch back to the legacy system before the 14:00 carrier pickup. Decision owner: Ana Ruiz.